Project Planning Phase

Project Planning Template (Product Backlog, Sprint Planning, Stories, Story points)

| Date: | 03 October 2026 |
| --- | --- |
| Team ID: | SWTID-2026-3257 |
| Project Name: | Implement Client Script & UI Policy (Incident Table) |
| Maximum Marks: | 5 Marks |

Product Backlog, Sprint Schedule, and Estimation (4 Marks)

Use the below template to create product backlog and sprint schedule for the Incident UI Policy and Client Script project:

| Sprint | Functional Requirement (Epic) | User Story Number | User Story / Task | Story Points | Priority | Team Members |
| --- | --- | --- | --- | --- | --- | --- |
| Sprint-1 | Dynamic UI Visibility | USN-1 | As a Service Desk Analyst, I want 'Resolution Code' and 'Resolution Notes' to appear only when State = 'Resolved', so that form clutter is minimized during initial logging. | 3 | High | Ayush |
| Sprint-1 | Mandatory Rules | USN-2 | As a Service Desk Analyst, I want 'Work Notes' and 'Assignment Group' to be mandatory for Priority 1 (Critical) tickets, ensuring full escalation tracking. | 3 | High | Team Member A |
| Sprint-1 | Priority Matrix Automation | USN-3 | As a Service Desk Analyst, I want Priority to auto-calculate dynamically when Impact or Urgency is changed, eliminating manual lookup errors. | 5 | High | Ayush |
| Sprint-1 | Form Security & Lock | USN-4 | As an Incident Manager, I want Closed incident records locked to Read-Only, preventing unauthorized historical edits. | 3 | High | Team Member B |
| Sprint-2 | Interactive Guidance | USN-5 | As a Service Desk Analyst, I want diagnostic prompts when selecting 'Hardware' or 'Network' categories, guiding standard troubleshooting. | 5 | Medium | Team Member A |
| Sprint-2 | UI Policy Declarative Rules | USN-6 | As a System Admin, I want UI policies configured declaratively without hardcoded scripts, ensuring easy ongoing maintenance. | 2 | Medium | Team Member B |
| Sprint-2 | Form Submit Validation | USN-7 | As an Incident Manager, I want onSubmit Client Scripts to validate caller and assigned group details before saving record payloads. | 3 | Medium | Ayush |
| Sprint-3 | Cross-Browser Verification | USN-8 | As a QA Lead, I want to verify client scripts and UI policies across Agent Workspace on Chrome, Edge, and Safari with zero JS errors. | 3 | High | Team Member A |
| Sprint-3 | Performance Optimization | USN-9 | As a System Admin, I want client-side script execution times to remain under 200ms to guarantee zero latency during high call volumes. | 2 | Medium | Team Member B |
| Sprint-4 | User Acceptance & Review | USN-10 | As a Product Owner, I want UAT sign-off from Service Desk leads before final release deployment to production instance. | 2 | High | Ayush |

Project Tracker, Velocity & Burndown Chart (4 Marks)

| Sprint | Total Story Points | Duration | Sprint Start Date | Sprint End Date (Planned) | Story Points Completed (as on Planned End Date) | Sprint Release Date (Actual) |
| --- | --- | --- | --- | --- | --- | --- |
| Sprint-1 | 14 | 6 Days | 05 Oct 2026 | 10 Oct 2026 | 14 | 10 Oct 2026 |
| Sprint-2 | 10 | 6 Days | 12 Oct 2026 | 17 Oct 2026 | 10 | 17 Oct 2026 |
| Sprint-3 | 5 | 6 Days | 19 Oct 2026 | 24 Oct 2026 | 5 | 24 Oct 2026 |
| Sprint-4 | 2 | 6 Days | 26 Oct 2026 | 31 Oct 2026 | 2 | 31 Oct 2026 |

Velocity Calculation

Velocity measures the amount of work a team can complete during a single sprint. For our team, across 4 sprints with a total of 31 completed story points over 24 working days:

• Total Story Points Delivered: 31 Points
• Total Sprints Completed: 4 Sprints (6 days per sprint)
• Average Velocity (AV) per Sprint = Total Points / Total Sprints = 31 / 4 = 7.75 Story Points / Sprint
• Average Velocity per Day = 31 / 24 = 1.29 Story Points / Day

Burndown Chart & Progress Explanation

A burndown chart is a graphical representation of remaining effort (work left to do) versus time across sprints. The planned ideal burn down rate decreases linearly from 31 story points to 0 story points over the 4 planned sprints.

| Sprint Milestone | Ideal Remaining Points | Actual Remaining Points | Status |
| --- | --- | --- | --- |
| Sprint Start (Day 0) | 31 Points | 31 Points | Backlog Initialized |
| End of Sprint-1 | 23.25 Points | 17 Points | Ahead of Schedule (-14 pts) |
| End of Sprint-2 | 15.5 Points | 7 Points | On Track (-10 pts) |
| End of Sprint-3 | 7.75 Points | 2 Points | Near Completion (-5 pts) |
| End of Sprint-4 | 0 Points | 0 Points | Fully Completed (-2 pts) |

References

• Agile Project Management Overview: https://www.atlassian.com/agile/project-management

• How to do Scrum with Jira Software: https://www.atlassian.com/agile/tutorials/how-to-do-scrum-with-jira-software

• Epics, Stories, and Story Points Estimation: https://www.atlassian.com/agile/project-management/estimation

• Burndown Charts in Agile Scrum: https://www.atlassian.com/agile/tutorials/burndown-charts

• Visual Paradigm Scrum Burndown Chart Guide: https://www.visual-paradigm.com/scrum/scrum-burndown-chart/